## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION XII - SOCCSSARGEN |  | CALENDAR YEAR: | 2024
PROVINCE: | COTABATO (NORTH COTABATO) |  | QUARTER: | 2
CITY/MUNICIPALITY: | ALEOSAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Financial Allocation for the KALAHI CIDDS NCDDP-AF equity on the prioritized projects | LGU-Aleosan, Cotabato | 4500000 | January 3, 2024 | August 30, 2024 | 96% | 4321714.29 |  | on-going
Economic Development
Opening of Municipal Streets / Barangay Roads | San Mateo, Aleosan, Cotabato | 1000000 | April 15, 2024 | June 28, 2024 | 60.72% | 607196 |  | On-going
Construction of Single/Double Barrel Box Culvert | New Leon, Aleosan, Cotabato | 1200000 | April 29, 2024 | July 28, 2024 | 100% | 1197824.88 |  | Completed
Livestock multiplier program for cattle | New Leon, Aleosan, Cotabato | 1000000 | June 8, 2024 | August 17, 2024 | 45% | 448001 |  | On-going
Construction of Market Building w/ Complete Facilities and Amenities | San Mateo, Aleosan, Cotabato | 4800000 | July 15, 2024 | November 29, 2024 | 86.21% | 4138267.54 |  | On-going
Completion of AA Slaughterhouse | San Mateo, Aleosan, Cotabato | 2500000 | June 8, 2024 | August 17, 2024 | 28.74% | 718600 |  | On-going
Installation of Solar Power Streetlights | San Mateo, Aleosan, Cotabato | 2000000 | April 29, 2024 | June 28, 2024 | 100% | 1299324.57 |  | Completed
Landbank Loan - Purchase of 3 units Dumptruck and 1 unit Backhoe Excavator | LGU-Aleosan, Cotabato | 6665003 | March 15, 2024 | November 29, 2024 | 45.8% | 3052513 |  | On-going
MDFO - DMAF Loan - Purchase of Backhoe Excavator | LGU-Aleosan, Cotabato | 1851215 | July 15, 2024 | November 29, 2024 | 50% | 925607.78 |  | On-going
Municipal Dev't. Fund Project (MDFP) Loan - Purchase of Rubber Seedlings for Rubber Based Farming System | LGU-Aleosan, Cotabato | 698769 | July 15, 2024 | November 29, 2024 | 50% | 349384.84 |  | On-going
Environmental Management
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| (SGD) ELVIN V. BOLIVAR |  |  |  | (SGD) EDUARDO C. CABAYA, MPA
| Local Budget Officer |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43