## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION XII - SOCCSSARGEN |  | CALENDAR YEAR: | 2024
PROVINCE: | COTABATO (NORTH COTABATO) |  | QUARTER: | 1
CITY/MUNICIPALITY: | ALEOSAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Economic Development
Construction of Market Building w/ Complete Facilities and Amenities | San Mateo, Aleosan, Cotabato | 1400000 | February 22, 2024 | March 28, 2024 | 100% | 1395103.1 |  | Completed
Opening of Municipal Streets / Barangay Roads | San Mateo, Aleosan, Cotabato | 1000000 | February 23, 2024 | June 28, 2024 | 4.98% | 49800 |  | On-going
Landbank Loan - Purchase of 3 units Dumptruck and 1 unit Backhoe Excavator | LGU-Aleosan, Cotabato | 6665003 | March 15, 2024 | November 29, 2024 | 16.97% | 1130756.35 |  | On-going
Environmental Management
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| ELVIN V. BOLIVAR |  |  |  | EDUARDO C. CABAYA, MPA
| Local Budget Officer |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43