## Form 7 - DFU (2)
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | REGION XII - SOCCSSARGEN |  | CALENDAR YEAR: | 2024
PROVINCE: | COTABATO (NORTH COTABATO) |  | QUARTER: | 3
CITY/MUNICIPALITY: | ALEOSAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development
Construction of Palacat IP Village Housing Project- Equity | Palacat, Aleosan, cotabato | 800000 | July 1, 2024 | December 31,2024 | 33.75% | 270000 |  | On-going
Economic Development
Opening of Municipal Streets / Barangay Roads | San Mateo, Aleosan, Cotabato | 1000000 | April 29, 2024 | July 28, 2024 | 100% | 999010.4 |  | Completed
Livestock multiplier program for cattle | New Leon, Aleosan, Cotabato | 1000000 | June 8, 2024 | December 31, 2024 | 49.17% | 491681 |  | On-going
Construction of Market Building w/ Complete Facilities and Amenities | San Mateo, Aleosan, Cotabato | 4800000 | July 15, 2024 | November 29, 2024 | 86.21% | 4138267.54 |  | On-going
Installation of Solar Power Streetlights | San Mateo, Aleosan, Cotabato | 2000000 | April 29, 2024 | June 28, 2024 | 100% | 1998342.4 |  | Completed
Landbank Loan - Purchase of 3 units Dumptruck and 1 unit Backhoe Excavator | LGU-Aleosan, Cotabato | 6665003 | March 15, 2024 | December 31, 2024 | 74.79% | 4984859.14 |  | On-going
DBP Loan Amortization for the Construction of Aleosan Commercial Complex | LGU-Aleosan, Cotabato | 991810.57 | July 1, 2024 | September 30,2024 | 100% | 991810.57 |  | Completed | 13603971.05
Environmental Management
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| (SGD) ELVIN V. BOLIVAR |  |  |  | (SGD) EDUARDO C. CABAYA, MPA
| Local Budget Officer |  |  |  | Local Chief Executive

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43