## PMR
LOCAL GOVERNMENT UNIT OF ALEOSAN | [11 empty] | Procurement Monitoring Report as of December 31, 2024
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
3000-10-6 | Supply & Delivery of Materials for the Construction of 30-Units Palacat IP Village Housing Project, Aleosan, Cotabato | LCE/MEO | No | Competitive Bidding | N/A | 2024-05-21 |  | 2024-05-29 | 2024-06-10 | 2024-06-10 | 20 | 2024-06-19 | 2024-06-19 | 2024-06-20 | 9 | 10 | 30 | 2024-06-21 | 2024-06-25 | 2024-06-26 | 5 | 36 | 2024-08-08 | 2024-08-09 | Government of the Philippines (current year's budget) | 3001700 |  | 3001700 | 3001131.02 |  | 3001131.02 | 0.00018955 | COA, End-Users, Observers | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-06-13 | 2024-06-13 | N/A |  | FALSE | FALSE
1000-2-35 | Construction of Slope Protection (Construction of Stone Masonry Slope Protection) at Municipal Hall Site, Brgy. San Mateo, Aleosan, Cotabato | LCE/MEO | No | Competitive Bidding | 2024-03-13 | 2024-03-20 |  | 2024-04-04 | 2024-04-16 | 2024-04-16 |  | 2024-04-23 | 2024-04-23 | 2024-04-24 |  |  |  | 2024-04-26 | 2024-05-06 | 2024-05-07 |  |  | 2024-07-02 | 2024-07-02 | Government of the Philippines (current year's budget) | 2000000 |  | 2000000 | 1999500 |  | 1999500 |  | COA, End-Users, Observers | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-16 | 2024-04-16 | N/A
1000-1-75 | Establishment of Permanent Evacuation Center (Electrification) at Brgy. New Leon, Aleosan, Cotabato | LCE/MEO | No | Competitive Bidding | N/A | 2024-04-16 |  | N/A | 2024-05-07 | 2024-05-07 | 21 | 2024-05-14 | 2024-05-14 | 2024-05-15 | 7 | 8 | 29 | 2024-05-17 | 2024-05-22 | 2024-05-27 | 10 | 41 | 2024-07-02 | 2024-07-02 | Government of the Philippines (current year's budget) | 639400 |  | 639400 | 638142.75 |  | 638142.75 | 0.0019663 | COA, End-Users, Observers | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-05-09 | 2024-05-09 | N/A |  | FALSE | FALSE
1000-2-5 | Construction of One (1) Unit Double Barrel Box Culvert at Barangay Tomado, Aleosan, Cotabato | LCE/MEO | No | Competitive Bidding | 2024-05-20 | 2024-05-21 | 1 | 2024-05-29 | 2024-06-10 | 2024-06-10 | 20 | 2024-06-19 | 2024-06-19 | 2024-06-20 | 9 | 10 | 30 | 2024-06-21 | 2024-06-27 | 2024-06-28 | 7 | 38 | 2024-10-02 | 2024-10-02 | Government of the Philippines (current year's budget) | 1500000 |  | 1500000 | 1498999.93 |  | 1498999.93 | 0.00066671 | COA, End-Users, Observers | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-06-13 | 2024-06-13 | N/A |  | FALSE | FALSE
1000-2-28 | Installation of Solar Power Streetlights (20 units) at Barangay San Mateo, Aleosan, Cotabato | LCE/MEO | No | Competitive Bidding | N/A | 2024-05-21 |  | N/A | 2024-06-10 | 2024-06-10 |  | 2024-06-19 | 2024-06-19 | 2024-06-20 |  |  |  | 2024-06-21 | 2024-06-27 | 2024-06-28 |  |  | 2024-07-08 | 2024-07-08 | Government of the Philippines (current year's budget) | 700000 |  | 700000 | 698999.93 |  | 698999.93 |  | COA, End-Users, Observers | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-06-13 | 2024-06-13 | N/A |  | FALSE | FALSE
1000-1-1 | Supply of Fuel and Lubricants for the period covered from July to December 2024 at the Office of Municipal Mayor, Aleosan, Cotabato | LCE/MEO | No | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | N/A | N/A |  | 2024-05-24 | 2024-06-05 | 2024-06-05 |  | 2024-06-19 | 2024-06-19 | 2024-06-20 | 14 | 15 |  | 2024-06-21 | 2024-06-27 | 2024-06-27 | 6 |  | 2024-07-05 | 2024-07-05 | Government of the Philippines (current year's budget) | 3000000 | 3000000 |  | 2777925 | 2777925 |  | 0.074025 | COA, End-Users, Observers | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-06-13 | 2024-06-13 | N/A |  | FALSE | FALSE
1000-1-14 | Supply of Fuel to the Office of Municipal Engineer to facilitate various projects/programs of LGU Aleosan, Cotabato | LCE/MEO | No | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | N/A | N/A |  | 2024-05-24 | 2024-06-05 | 2024-06-05 |  | 2024-06-19 | 2024-06-19 | 2024-06-20 | 14 | 15 |  | 2024-06-21 | 2024-06-27 | 2024-06-27 | 6 |  | 2024-07-09 | 2024-07-09 | Government of the Philippines (current year's budget) | 680000 | 680000 |  | 679500 | 679500 |  | 0.00073529 | COA, End-Users, Observers | 2024-05-17 | 2024-05-17 | 2024-05-17 | 2024-06-13 | 2024-06-13 | N/A |  | FALSE | FALSE
8000-1-2-2 | Supply and Delivery of 88 sacks of Livestock Feeds/Concentrate for LGU Stock Farm, Aleosan, Cotabato | OMAG | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-05 |  | N/A | 2024-06-10 | 2024-06-10 |  | 2024-06-10 | N/A | 2024-06-14 |  |  |  | 2024-06-18 | 2024-06-26 | 2024-06-27 |  |  | 2024-07-08 | 2024-07-08 | Government of the Philippines (current year's budget) | 74976 | 74976 |  | 74800 | 74800 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
8000-1-2-2 | Supply and Delivery of 30 pcs. of 200 Liters Storage Drums for Livestock concentrate in LGU Stock Farm, Aleosan, Cotabato | OMAG | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-05 |  | N/A | 2024-06-13 | 2024-06-13 | 8 | 2024-06-13 | N/A | 2024-06-14 |  | 1 | 9 | 2024-06-18 | 2024-06-26 | 2024-06-27 | 9 | 22 | 2024-08-06 | 2024-08-06 | Government of the Philippines (current year's budget) | 75000 | 75000 |  | 74700 | 74700 |  | 0.004 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
1000-1-14 | Supply and Delivery of 8 pcs. of tires for the maintenance of three (3) units HOWO Dumptruck at LGU Aleosan, Cotabato | LCE/MEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-12 |  | N/A | 2024-06-10 | 2024-06-10 |  | 2024-06-10 | N/A | 2024-06-14 |  |  |  | 2024-06-18 | 2024-07-05 | 2024-07-05 |  |  | 2024-07-09 | 2024-07-09 | Government of the Philippines (current year's budget) | 132000 | 132000 |  | 128000 | 128000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1000-1-14 | Supply and Delivery of Transmission Assembly, Converter and Cylinder Boom for the maintenance of Payloader of LGU Aleosan, Cotabato | LCE/MEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-12 |  | N/A | 2024-06-13 | 2024-06-13 |  | 2024-06-13 | N/A | 2024-06-14 |  |  |  | 2024-06-18 | 2024-07-15 | 2024-07-15 |  |  | 2024-07-30 | 2024-07-30 | Government of the Philippines (current year's budget) | 106315 | 106315 |  | 105000 | 105000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1000-1-14 | Supply and Delivery of Spare Parts for the repair and maintenance of Grader 2, LGU Aleosan, Cotabato | LCE/MEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-12 |  | N/A | 2024-06-19 | 2024-06-19 |  | 2024-06-19 | N/A | 2024-06-20 |  |  |  | 2024-06-21 | 2024-07-05 | 2024-07-05 |  |  | 2024-07-15 | 2024-07-15 | Government of the Philippines (current year's budget) | 132600 | 132600 |  | 128000 | 128000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1000-1-79 | Supply and Delivery of Multivitamins, Medicines and Medical Supplies at Municipal Health Office, LGU Aleosan, Cotabato | MHO | No | Competitive Bidding | N/A | 2024-06-14 |  | N/A | 2024-07-04 | 2024-07-04 | 20 | 2024-07-16 | 2024-07-16 | 2024-07-29 | 12 | 25 | 45 | 2024-07-30 | 2024-08-12 | 2024-08-19 | 20 | 66 | 2024-09-09 | 2024-09-09 | Government of the Philippines (current year's budget) | 246200 | 246200 |  | 237513 | 237513 |  | 0.035284 | COA, End-Users, Observers | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-07-09 | 2024-07-09 | N/A |  | FALSE | FALSE
1000-1-75 | Supply & Delivery of Materials for the Establishment of Permanent Evacuation Center (Construction of Kitchen, Canopy and Comfort Room, Rehab. of Doors, Windows, Roll-up, Water Lines & Electrical Wires) at Barangay New Leon, Aleosan, Cotabato | MDRRM/MEO | No | Competitive Bidding | N/A | 2024-07-05 |  | N/A | 2024-07-29 | 2024-07-29 | 24 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 8 | 8 | 32 | 2024-08-07 | 2024-08-08 | 2024-08-15 | 8 | 41 | 2024-08-21 | 2024-08-21 | Government of the Philippines (current year's budget) | 867400 |  | 867400 | 865630 |  | 865630 | 0.0020406 | COA, End-Users, Observers | 2024-07-09 | 2024-07-09 | 2024-07-09 | 2024-07-30 | 2024-07-30 | N/A |  | FALSE | FALSE
1000-1-61 | Supply and Delivery of Materials for the Retrofitting/Rehabilitation of RHU Building (Retrofitting of Pantry Area (2 units), Repainting of Ceiling & Walls & Rehab. of Roofing and Ceiling Eaves at Municipal Hall Site, LGU Aleosan, Barangay San Mateo, Aleosan, Cotabato | MHO | No | Competitive Bidding | N/A | 2024-07-05 |  | N/A | 2024-07-29 | 2024-07-29 | 24 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 8 | 8 | 32 | 2024-08-07 | 2024-08-08 | 2024-08-15 | 8 | 41 | 2024-08-21 | 2024-08-21 | Government of the Philippines (current year's budget) | 293100 |  | 293100 | 291783 |  | 291783 | 0.0044933 | COA, End-Users, Observers | 2024-07-09 | 2024-07-09 | 2024-07-09 | 2024-07-30 | 2024-07-30 | N/A |  | FALSE | FALSE
1000-2-24 | Supply and Delivery of Materials for the Development of Water Source at Barangay New Leon, Aleosan, Cotabato | MEO | No | Competitive Bidding | N/A | 2024-07-16 |  | N/A | 2024-08-28 | 2024-08-28 |  | 2024-09-11 | 2024-09-11 | 2024-09-11 |  |  |  | 2024-09-12 | 2024-10-04 | 2024-10-24 |  |  | 2024-11-05 | 2024-11-06 | Government of the Philippines (continuing budget) | 230300 |  | 230300 | 230300 |  | 230300 |  | COA, End-Users, Observers | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-29 | 2024-08-29 | N/A
1000-2-24 | Supply and Delivery of Materials for the Development of Water Source at Barangay Upper Mingading, Aleosan, Cotabato | MEO | No | Competitive Bidding | N/A | 2024-08-07 |  | N/A | 2024-08-28 | 2024-08-28 |  | 2024-09-04 | 2024-09-04 | 2024-09-11 |  |  |  | 2024-09-12 | 2024-10-04 | 2024-10-24 |  |  | 2024-11-05 | 2024-11-06 | Government of the Philippines (continuing budget) | 278700 |  | 278700 | 278700 |  | 278700 |  | COA, End-Users, Observers | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-29 | 2024-08-29 | N/A
1000-2-20 | Supply of Plumbing materials for the Expansion of Water System Pipelines (Repair and Maintenance of Water System Distribution Lines at Public Market, Barangay San Mateo, Aleosan, Cotabato | MEO | No | Competitive Bidding | N/A | 2024-08-07 |  | N/A | 2024-08-28 | 2024-08-28 | 21 | 2024-09-04 | 2024-09-04 | 2024-09-05 | 7 | 8 | 29 | 2024-09-09 | 2024-10-08 | 2024-10-16 | 37 | 70 | 2024-11-04 | 2024-11-06 | Government of the Philippines (continuing budget) | 278800 |  | 278800 | 278060 |  | 278060 | 0.0026542 | COA, End-Users, Observers | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-29 | 2024-08-29 | N/A |  | FALSE | FALSE
1000-2-18 | Supply and Delivery of Materials for the Construction of Multi-Purpose Drying Pavement at Aleosan, Cotabato | MEO | No | Competitive Bidding | N/A | 2024-07-31 |  | N/A | 2024-08-20 | 2024-08-20 | 20 | 2024-08-28 | 2024-08-28 | 2024-08-29 | 8 | 9 | 29 | 2024-08-30 | 2024-09-11 | 2024-09-12 | 13 | 43 | 2024-09-18 | 2024-09-18 | Government of the Philippines (current year's budget) | 670300 |  | 670300 | 669800 |  | 669800 | 0.00074593 | COA, End-Users, Observers | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-21 | 2024-08-21 | N/A |  | FALSE | FALSE
1000-1-14 | Supply & Delivery of Tires & Battery Plates for the maintenance of Municipal Heavy Equipment & Light Transportation Vehicle of LGU Aleosan, Cotabato | MEO | No | Competitive Bidding | N/A | 2024-08-07 |  | N/A | 2024-08-27 | 2024-08-27 |  | 2024-09-04 | 2024-09-04 | 2024-09-11 |  |  |  | 2024-09-12 | 2024-10-07 | 2024-10-09 |  |  | 2024-10-15 | 2024-10-15 | Government of the Philippines (current year's budget) | 694200 | 694200 | 0 | 496200 | 496200 | 0 |  | COA, End-Users, Observers | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-29 | 2024-08-29 | N/A
3000-3-6 | Supply & Delivery of assorted goods for Gift-giving of Indigent PWD Members at Aleosan, Cotabato | PWD | No | Competitive Bidding | N/A | 2024-08-07 |  | N/A | 2024-08-27 | 2024-08-27 |  | 2024-09-04 | 2024-09-04 | 2024-09-11 |  |  |  | 2024-09-12 | 2024-10-09 | 2024-10-10 |  |  | 2024-11-09 | 2024-11-09 | Government of the Philippines (current year's budget) | 269900 | 269900 |  | 269575.2 | 269575.2 |  |  | COA, End-Users, Observers | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-29 | 2024-08-29 | N/A
1000-1-5 | Publication of Municipal Ordinance No. 23-96 & 24-97 of the Municipality of Aleosan, Cotabato | SB | No | NP-53.9 - Small Value Procurement | N/A | 2024-07-04 |  | N/A | 2024-07-09 | 2024-07-09 |  | N/A | N/A | 2024-07-17 |  |  |  | 2024-07-30 | 2024-08-01 | 2024-08-02 |  |  | 2024-08-15 | 2024-08-16 | Government of the Philippines (current year's budget) | 79980 |  | 79980 | 79980 |  | 79980 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1000-3-15 | Supply and Delivery of materials for Closure of Dumpsite (Perimeter Fence with Steel Gate at Old Dumpsite at Barangay San Mateo, Aleosan, Cotabato | MEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-07-05 |  | N/A | 2024-07-09 | 2024-07-09 | 4 | N/A | N/A | 2024-07-17 |  | 8 | 12 | 2024-07-30 | 2024-08-09 | 2024-08-12 | 13 | 38 | 2024-08-16 | 2024-08-16 | Government of the Philippines (current year's budget) | 199670 |  | 199670 | 199270 |  | 199270 | 0.0020033 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
8000-1-2-4 | Supply and Delivery of Forage Chopper for LGU Livestock Multiplier Farm at Aleosan, Cotabato | OMAG | No | NP-53.9 - Small Value Procurement | N/A | 2024-08-22 |  | N/A | 2024-08-28 | 2024-08-28 | 6 | N/A | N/A | 2024-08-29 |  | 1 | 7 | 2024-09-03 | 2024-09-10 | 2024-09-11 | 8 | 20 | 2024-09-16 | 2024-09-16 | Government of the Philippines (current year's budget) | 100000 |  | 100000 | 99960 |  | 99960 | 0.0004 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
8000-1-2-2 | Supply and Delivery of 176 sacks of Livestock Feeds/Concentrate for LGU Stock Farm, Aleosan, Cotabato | OMAG | No | NP-53.9 - Small Value Procurement | N/A | 2024-08-22 |  | N/A | 2024-08-28 | 2024-08-28 |  | N/A | N/A | 2024-08-29 |  |  |  | 2024-09-03 | 2024-09-10 | 2024-09-11 |  |  | 2024-09-16 | 2024-09-16 | Government of the Philippines (current year's budget) | 149952 |  | 149952 | 149600 |  | 149600 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1000-2-31 | Supply and delivery of materials use for construction/retrofit of drainage system and slope protection (installation of 48” RCP culvert) at Barangay San Mateo, Aleosan, Cotabato | MEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-09-06 |  | N/A | 2024-09-11 | 2024-09-11 |  | N/A | N/A | 2024-09-12 |  |  |  | 2024-09-13 | 2024-09-30 | 2024-10-01 |  |  | 2024-10-14 | 2024-10-15 | Government of the Philippines (current year's budget) | 101300 |  | 101300 | 100500 |  | 100500 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1000-1-1 | Supply of Materials for the Building Maintenance (Rectify of Facilities or SGLG Compliance, Aleosan Municipal Hall Building Barangay San Mateo, Aleosan, Cotabato | LCE/MEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-09-11 |  | N/A | 2024-09-16 | 2024-09-16 |  | N/A | N/A | 2024-09-16 |  |  |  | 2024-09-17 | 2024-09-30 | 2024-10-01 |  |  | 2024-10-14 | 2024-10-15 | Government of the Philippines (current year's budget) | 102393 | 102393 |  | 101470 | 101470 |  |  | N/A | N/A | N/A | N/A | N/A | N/A
1000-2-26, 1000-2-27 | Construction/Expansion/Rehabilitation of Potable Water Supply System (Installation of Solar Panel and Construction of Perimeter Fence (TOUWA) at Barangay San Mateo, Aleosan, Cotabato | MEO | No | Competitive Bidding | 2024-07-29 | 2024-08-07 |  | 2024-08-15 | 2024-08-27 | 2024-08-27 |  | 2024-09-04 | 2024-09-04 | 2024-09-05 |  |  |  | 2024-09-09 | 2024-09-17 | 2024-09-20 |  |  | 2024-11-06 | 2024-11-06 | Government of the Philippines (current year's budget) | 2700000 |  | 2700000 | 2697998.26 |  | 2697998.26 |  | COA, End-Users, Observers | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-29 | 2024-08-29 | N/A
1000-2-1 | Concreting of 300m Farm to Market Road at Barangay San Mateo, Aleosan, Cotabato | MEO | No | Competitive Bidding | 2024-07-29 | 2024-08-07 |  | 2024-08-15 | 2024-08-27 | 2024-08-27 |  | 2024-09-04 | 2024-09-04 | 2024-09-11 |  |  |  | 2024-09-12 | 2024-09-17 | 2024-09-24 |  |  | 2024-12-04 | 2024-12-04 | Government of the Philippines (current year's budget) | 3000000 |  | 3000000 | 2998986.25 |  | 2998986.25 |  | COA, End-Users, Observers | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-29 | 2024-08-29 | N/A
| Supply and Delivery of Materials for the Dole Integrated Livelihood Program (DILP) individual starter kit (Agricultural equipment, ICT Equipment & Office Supplies, Gardening, Cookery, Events Management & Party Supplies, Automotive and Carpentry) at Aleosan, Cotabato | PESO | No | Competitive Bidding | N/A | 2024-10-03 |  | 2024-10-11 | 2024-10-23 | 2024-10-23 |  | 2024-10-30 | 2024-10-30 | 2024-10-30 |  |  |  | 2024-10-31 | 2024-11-06 | 2024-11-08 |  |  | 2024-12-08 | 2024-12-08 | Government of the Philippines (current year's budget) | 1248470 |  | 1248470 | 1247276.68 |  | 1247276.68 |  | COA, End-Users, Observers | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2024-10-23 | 2024-10-23 | N/A
| Supply and Delivery of Materials for the Dole Integrated Livelihood Program (DILP) individual starter kit (Bakery, Hardware, Car Washing Equipment) at Aleosan, Cotabato | PESO | No | Competitive Bidding | N/A | 2024-10-03 |  | 2024-10-11 | 2024-10-23 | 2024-10-23 |  | 2024-10-30 | 2024-10-30 | 2024-10-30 |  |  |  | 2024-10-31 | 2024-11-06 | 2024-11-08 |  |  | 2024-11-27 | 2024-11-27 | Government of the Philippines (current year's budget) | 1373740 |  | 1373740 | 1372360 |  | 1372360 |  | COA, End-Users, Observers | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2024-10-23 | 2024-10-23 | N/A
1000-2-50 | Supply and delivery of materials use for establishment/construction of new public cemetery (Site preparation and construction of perimeter fence 100 meters) at Barangay Katalicanan, Aleosan, Cotabato | MEO | No | Competitive Bidding | N/A | 2024-09-06 |  | N/A | 2024-09-26 | 2024-09-26 |  | 2024-10-10 | 2024-10-10 | 2024-10-14 |  |  |  | 2024-10-15 | 2024-10-31 | 2024-11-04 |  |  | 2024-11-06 | 2024-11-06 | Government of the Philippines (current year's budget) | 369855 |  | 369855 | 369580 |  | 369580 |  | COA, End-Users, Observers | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-10-04 | 2024-10-04 | N/A
3000-10-6 | Supply and delivery of materials use for Construction of Palacat IP Village Housing Project at Barangay Palacat, Aleosan, Cotabato | LCE/MEO | No | Competitive Bidding | N/A | 2024-09-13 |  | N/A | 2024-10-03 | 2024-10-03 |  | 2024-10-10 | 2024-10-10 | 2024-10-14 |  |  |  | 2024-10-15 | 2024-10-31 | 2024-11-04 |  |  | 2024-11-06 | 2024-11-06 | Government of the Philippines (current year's budget) | 529056 |  | 529056 | 528856.87 |  | 528856.87 |  | COA, End-Users, Observers | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-10-04 | 2024-10-04 | N/A
8000-1-2-11 | Supply & Delivery of Materials for the Livelihood Program - Swine Breeding Project (Construction of Swine Shed, Drainage Canal and Septic Vault) at Barangay Cawilihan, Aleosan, Cotabato | MEO | No | Competitive Bidding | N/A | 2024-09-25 |  | N/A | 2024-10-15 | 2024-10-15 |  | 2024-10-28 | 2024-10-28 | 2024-10-30 |  |  |  | 2024-11-04 | 2024-11-25 | 2024-11-26 |  |  | 2024-11-29 | 2024-11-29 | Government of the Philippines (current year's budget) | 315470 |  | 315470 | 315280 |  | 315280 |  | COA, End-Users, Observers | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-21 | 2024-10-21 | N/A
8000-1-3-3 | Purchase of Feeds and Nets for the Establishment of Tilapia Hatchery at Aleosan, Cotabato | OMAG | No | NP-53.9 - Small Value Procurement | N/A | 2024-10-10 |  | N/A | 2024-10-15 | 2024-10-15 |  | N/A | N/A | 2024-10-15 |  |  |  | 2024-10-25 | 2024-10-31 | 2024-11-04 |  |  | 2024-11-25 | 2024-11-25 | Government of the Philippines (current year's budget) | 81000 |  | 81000 | 81000 |  | 81000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3000-4-2 | Supply & Delivery of assorted goods for Gift-giving of Indigent & Bedridden Senior Citizens at Aleosan, Cotabato | SENIOR CITIZEN | No | NP-53.9 - Small Value Procurement | N/A | 2024-11-07 |  | N/A | 2024-11-11 | 2024-11-11 |  | N/A | N/A | 2024-11-12 |  |  |  | 2024-11-13 | 2024-11-20 | 2024-11-21 |  |  | 2024-11-29 | 2024-11-29 | Government of the Philippines (current year's budget) | 99900 | 99900 |  | 99866 | 99866 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1000-2-2 | Supply of Item 104/Filling Materials (Price at Source to be hauled by LGU Equipments) for the Opening of Municipal Streets/Barangay Road at Barangay Tomado, Aleosan, Cotabato | LCE/MEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-11-26 |  | N/A | 2024-11-29 | 2024-11-29 |  | N/A | N/A | 2024-12-02 |  |  |  | 2024-12-03 | 2024-12-04 | 2024-12-05 |  |  | 2024-12-09 | 2024-12-09 | Government of the Philippines (current year's budget) | 199800 | 199800 |  | 198801 | 198801 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3000-3-3 | Provision of Livelihood Equipment/ Machines to PWD at Aleosan, Cotabato | PWD | No | NP-53.9 - Small Value Procurement | N/A | 2024-11-16 |  | N/A | 2024-11-19 | 2024-11-19 |  | N/A | N/A | 2024-11-26 |  |  |  | 2024-11-27 | 2024-12-06 | 2024-12-07 |  |  | 2024-12-22 | 2024-12-26 | Government of the Philippines (current year's budget) | 100000 | 0 | 100000 | 94000 | 0 | 94000 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1000-2-24, 1000-2-20 | Supply of materials use for Improvement and Expansion of Water System at Barangay San Mateo, Aleosan, Cotabato | MEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-11-26 |  | N/A | 2024-11-29 | 2024-11-29 | 3 | N/A | N/A | 2024-12-02 |  | 3 | 6 | 2024-12-03 | 2024-12-10 | 2024-12-11 | 8 | 15 | 2024-12-13 | 2024-12-13 | Government of the Philippines (continuing budget) | 169524 | 169524 |  | 168550 | 168550 |  | 0.0057455 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | FALSE | FALSE
[25 empty] | Total Allotted Budget of Procurement Activities | 26791001 | 5982808 | 20808193 |  |  |  | 1.737%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 26325594.89 | 5539900.2 | 20785694.69
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 465406.11 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
1000-2-21 | Completion of AA Slaughter House (Construction of Waste Water Treatment Facility, Provision of Gen. Set & Perimeter Fence) at Barangay San Mateo, Aleosan, Cotabato | LCE/MEO | No | Competitive Bidding | N/A | 2024-08-07 |  | 2024-08-15 | 2024-08-27 | 2024-08-27 | 20 | 2024-09-04 | 2024-09-04 | 2024-09-11 | -48 | 10 | 30 | 2024-09-12 | 2024-09-17 | 2024-09-24 | 12 | 48 | N/A | 2024-12-04 | Government of the Philippines (current year's budget) | 1700000 |  | 1700000 | 1697499.51 |  | 1697499.51 | 0.0014709 | COA,Observer, End User | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2024-08-29 | 2024-08-29 | N/A |  | 0
3000-1-1 | Construction of Municipal Health Facilities (Construction of OPD Facility and Concrete Perimeter Fence) at LGU Aleosan, Barangay San Mateo, Aleosan, Cotabato | MHO | No | Competitive Bidding | N/A | 2024-08-09 |  | 2024-08-22 | 2024-09-03 | 2024-09-03 | 25 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 15 | 15 | 40 | 2024-09-20 | 2024-09-27 | 2024-09-30 | 10 | 52 | N/A | 2024-12-04 | Government of the Philippines (current year's budget) | 1000000 |  | 1000000 |  |  | 998788.32 | - | COA,Observer, End User | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2024-09-10 | 2024-09-10 | N/A |  | 0
1000-2-9 | Construction of Aleosan Commercial Complex (Construction of 1 Unit 2-Storey Commercial Building, 4 Units 1-Storey Commercial Building and Renovation of Existing 2-Storey Commercial Building) | LCE | No | Competitive Bidding | 2023-08-02 | 2023-08-04 | 2 | 2023-08-22 | 2023-09-04 | 2023-09-04 | 31 | 2023-09-12 | 2023-09-11 | 2023-09-20 | 7 | 16 | 47 | 2023-10-12 | 2023-10-17 | 2023-10-23 | 11 | 80 | N/A | 2024-12-12 | Loan from Development Bank of the Philippines | 150000000 |  | 150000000 |  |  | 149712852.31 | - | COA,Observer, End User | 2023-08-04 | 2023-08-04 | 2023-08-04 | 2023-09-04 | 2023-09-04 | N/A |  | 0
-
[11 empty] | 2024-06-10 | [20 empty] | -
-
[7 empty] | 2 | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 152700000 | 0 | 152700000 | 1697499.51 | 0 | 152409140.14 | 0.1471%
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [16 empty] | APPROVED:
|  | FLORA JEAN C. MIRANO | [9 empty] | ELVIN V. BOLIVAR | [16 empty] | EDUARDO C. CABAYA
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Head of the Procuring Entity

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 28023094.4
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 42
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 24 | 3 | 0.125 | 246 | 0.125 | 127 | 5.2917 | 373 | 15.5417 | 141 | 5.875 | 556 | 23.1667
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.1 Two Failed Biddings | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.2 Emergency Cases | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 16 | 0 | 0 | 21 | 0 | 13 | 0.8125 | 34 | 2.125 | 38 | 2.375 | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 2 | 0 | 0 | 0 | 0 | 30 | 15 | 0 | 0 | 12 | 6 | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 42 | 0.13043 | 0.041667 | 11.6087 | 0.041667 | 7.3913 | 7.0347 | 17.6957 | 5.8889 | 8.3043 | 4.75 | 24.1739 | 7.7222
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 24 | 24 | 173906591 | 22682172.4 | 100% | 13.04% | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 0 | 0 | 0 | 0 |  |  | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.2 Emergency Cases | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 16 | 16 | 1904410 | 1883497 | 100% | 98.9% | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 2 | 2 | 3680000 | 3457425 | 100% | 93.95% | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 42 | 42 | 179491001 | 179491001 | 100% | 68.63% | 0 | 0
Total for Alternative Mode of Procurement | 18 | 18 | 5584410 | 5340922 | 100% | 96.43% | 0 | 0
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Completed | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Failed | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Ongoing | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0!
Total | 0 | 0% | 0 | 0% | 0 | #DIV/0! | #DIV/0!
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 0%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 0%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 0 | 0
Regular Procurement | 42 | 179491001
Total | 42 | 179491001
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | 0%
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 0 | 0 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 0 | 0 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 0 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell